## Tasks
Multi-Initiative Resource Allocation & Prioritization Tracker
Task-level log across three concurrent initiatives sharing a common Budget / Staff-Hour / Vendor-Slot pool for the quarter
Task ID | Initiative | Task Name | Owner | Start Date | Deadline | Impact (1-5) | Urgency (1-5) | Priority Score | Priority Rank | Status | Budget Required (Rs.) | Staff Hours Required | Vendor Slots Required
1 | Product Launch - SolarX | Finalize product packaging design | Rahul | 2026-09-01 | 2026-09-20 | 5 | 5 | 25 | 1 | In Progress | 40000 | 30 | 2
2 | Product Launch - SolarX | Vendor selection for print material | Rahul | 2026-09-05 | 2026-09-25 | 4 | 4 | 16 | 9 | Planned | 25000 | 15 | 3
3 | Product Launch - SolarX | Launch event venue booking | Priya | 2026-09-10 | 2026-10-05 | 5 | 3 | 15 | 14 | In Progress | 80000 | 20 | 2
4 | Product Launch - SolarX | Social media campaign setup | Sneha | 2026-09-08 | 2026-10-01 | 4 | 5 | 20 | 5 | In Progress | 30000 | 40 | 1
5 | Product Launch - SolarX | Product demo video production | Aman | 2026-09-12 | 2026-10-10 | 3 | 4 | 12 | 16 | Planned | 60000 | 35 | 2
6 | Product Launch - SolarX | Press release drafting | Priya | 2026-09-15 | 2026-09-28 | 3 | 5 | 15 | 15 | Completed | 5000 | 10 | 0
7 | Product Launch - SolarX | Influencer outreach | Sneha | 2026-09-18 | 2026-10-08 | 4 | 3 | 12 | 17 | Planned | 45000 | 20 | 1
8 | Product Launch - SolarX | Post-launch feedback survey | Aman | 2026-10-15 | 2026-10-30 | 2 | 2 | 4 | 21 | Cancelled | 8000 | 12 | 0
9 | Campus Hiring Drive | Shortlist target campuses | Karan | 2026-09-01 | 2026-09-12 | 4 | 4 | 16 | 10 | Completed | 5000 | 25 | 0
10 | Campus Hiring Drive | Prepare JD and assessment test | Karan | 2026-09-03 | 2026-09-15 | 4 | 5 | 20 | 6 | Completed | 3000 | 20 | 0
11 | Campus Hiring Drive | Book campus visit logistics | Nisha | 2026-09-10 | 2026-10-01 | 3 | 3 | 9 | 19 | In Progress | 60000 | 30 | 4
12 | Campus Hiring Drive | Conduct pre-placement talks | Nisha | 2026-09-20 | 2026-10-10 | 4 | 4 | 16 | 11 | Planned | 10000 | 40 | 0
13 | Campus Hiring Drive | Schedule interview panels | Karan | 2026-09-25 | 2026-10-15 | 5 | 5 | 25 | 2 | Planned | 2000 | 35 | 0
14 | Campus Hiring Drive | Offer letter processing | Nisha | 2026-10-16 | 2026-10-25 | 3 | 4 | 12 | 18 | Planned | 1000 | 15 | 0
15 | Campus Hiring Drive | Onboarding kit preparation | Karan | 2026-10-20 | 2026-11-05 | 2 | 2 | 4 | 22 | Cancelled | 20000 | 18 | 2
16 | Campus Hiring Drive | Post-drive feedback report | Nisha | 2026-11-01 | 2026-11-10 | 2 | 1 | 2 | 24 | Planned | 0 | 10 | 0
17 | Annual Partner Meet | Venue shortlisting and booking | Meera | 2026-09-01 | 2026-09-20 | 5 | 5 | 25 | 3 | In Progress | 150000 | 25 | 3
18 | Annual Partner Meet | Catering vendor finalization | Meera | 2026-09-15 | 2026-10-05 | 4 | 4 | 16 | 12 | Planned | 70000 | 15 | 2
19 | Annual Partner Meet | Guest list and invites | Vikram | 2026-09-10 | 2026-10-01 | 4 | 5 | 20 | 7 | In Progress | 8000 | 20 | 0
20 | Annual Partner Meet | Stage and AV setup coordination | Vikram | 2026-10-01 | 2026-10-25 | 5 | 4 | 20 | 8 | Planned | 90000 | 25 | 3
21 | Annual Partner Meet | Travel and accommodation for guests | Meera | 2026-10-05 | 2026-10-28 | 4 | 4 | 16 | 13 | Planned | 100000 | 30 | 2
22 | Annual Partner Meet | Event day run-sheet planning | Vikram | 2026-10-20 | 2026-11-02 | 5 | 5 | 25 | 4 | Planned | 5000 | 25 | 0
23 | Annual Partner Meet | Gifting and merchandise sourcing | Meera | 2026-09-20 | 2026-10-10 | 3 | 3 | 9 | 20 | In Progress | 35000 | 12 | 2
24 | Annual Partner Meet | Post-event feedback and report | Vikram | 2026-11-03 | 2026-11-12 | 2 | 2 | 4 | 23 | Planned | 0 | 10 | 0

## Resource Capacity
Shared Resource Pool - Quarter Capacity
Edit the yellow cells to test different capacity scenarios
Resource Type | Total Available (Quarter) | Unit
Budget | 500000 | Rs.
Staff Hours | 550 | hrs
Vendor Slots | 35 | slots

## Allocation Tracker
Resource Allocation & Bottleneck Tracker
Allocated = sum of all non-Cancelled tasks in Tasks sheet
Resource Type | Total Available | Allocated (Active Tasks) | Utilization % | Bottleneck Flag
Budget | 500000 | 824000 | 164.8% | Over-allocated
Staff Hours | 550 | 507 | 92.18% | Near Capacity
Vendor Slots | 35 | 27 | 77.14% | Healthy
Allocation by Initiative (active tasks only)
Initiative | Budget Allocated (Rs.) | Staff Hours Allocated | Vendor Slots Allocated
Product Launch - SolarX | 285000 | 170 | 11
Campus Hiring Drive | 81000 | 175 | 4
Annual Partner Meet | 458000 | 162 | 12

## Dashboard
Resource Allocation Dashboard
Total Active Tasks | 22
Cancelled Tasks | 2
Resources Over-Allocated | 1
Resource | Utilization % |  | Status | Task Count | Initiative | Budget Allocated
Budget | 164.8% |  | In Progress | 7 | Product Launch - SolarX | 285000
Staff Hours | 92.18% |  | Planned | 12 | Campus Hiring Drive | 81000
Vendor Slots | 77.14% |  | Completed | 3 | Annual Partner Meet | 458000
|  |  | Cancelled | 2
Top 5 Priority Tasks (Recommended Resource Allocation Order)
Rank | Task Name | Initiative | Priority Score | Status
1 | Finalize product packaging design | Product Launch - SolarX | 25 | In Progress
2 | Schedule interview panels | Campus Hiring Drive | 25 | Planned
3 | Venue shortlisting and booking | Annual Partner Meet | 25 | In Progress
4 | Event day run-sheet planning | Annual Partner Meet | 25 | Planned
5 | Social media campaign setup | Product Launch - SolarX | 20 | In Progress